## Sheet1
Roundy COST PROJECTION:
TIMELINE = 3 months to shipping date |  |  | EXPENSE or
COMPONENT | HOURS | rate/hr | MATERIAL | LABOR | SUBTOTAL
| design work by LAD at hourly wage of | 35
Finish designing, drawing gasifier details, CNC cutout drawings | 15 | 35 |  | 525
Finish fabrication instructions, Specs, BOM, further drawings for OSE | 25 | 35 |  | 875
component details, vendor, model, etc., order components | 20 | 35 |  | 700
Oversee parts fabrication, assembly, get materials | 100 | 35 |  | 3500
draw detailed mold-assembly drawings | 20 | 35 |  | 700
video documentation of daily details of construction, edit, post | 30 | 35 |  | 1050
7350
stainless steel sheets |  |  | 3469.52
stainless stovepipe, including bypass + unions & elbows |  |  | 227
material for molds, rental of mixer, vibrator |  |  | 440
Castable low-water/low-cement refractory - 650lb@$0.87/lb + tax, shipping |  |  | 776
other metal - stainless pipe, bolts, latches, hardware, water valves, pressure valve |  |  | 380
thermocouples, gasketing, Neoceram window |  |  | 325
kaowool & mineral insulation blanket, dampers, hardware |  |  | 385
variable-speed fan |  |  | 285
Bacharach PCA-3 225 combustion analyser |  |  | 1640
water pump - Grundfoose max 6.3gpm, max 5.1ft head |  |  | 420
miscellaneous expenses |  |  | 900 |  | Skagit River Steel bid is $4,265.30 more than Alaskan Copper
plasma-cutting of most parts |  |  | 800 |  | laser-cut bid | 9534
Firing of refractory parts in kiln |  |  | 150 |  | plasma-cut#2 | 8905.9
rental of metal shop, welding, forming, assistant, for 3 mo. | 55 | 40 | 850 | 3050
assemble molds, rent mixer & cast ceramic parts | 40 | 35 |  | 1400
Start-up; Burn-in, procure & test various fuels, log, analyse data | 80 | 35 |  | 2800
troubleshoot system, optimize components | 50 | 35 |  | 1750 | 9000
boxing, transporting to shipping terminal, shipping to Factor-E-Farm |  |  | 1000 |  | 12047.52
TOTAL: | 435 |  | 12047.52 | 16350
GRAND TOTAL: |  |  |  |  | 28397.52
LAD TOTAL = | 380 | hrs/wk = | 31.6667
producing a 110,000 Btu/hr gasifier, with gasification air preheat/producer-gas-cooling HX, ash-removal
prices below from Western Industrial Ceramics 1-800-727-9424 talked with Chuck Noble
Sparcast LC-32-AL = 175lb/ft3, in 55lb bags $0.87/lb = $47.85/bag + tax + pallet delivery to residential area = $135 + Ferry
600 lb needed for castings = 10.9 bags = $526+
1" x 48" x 25' roll of Unifrax ceramic insulation (8lb density) | 140
1/4" gasket paper ~ 50" x 44" piece | 26.7
for ceramic hearth seal, 1" fiber rope best, or use 2 layers of 3/4" braided = 127" long (11ft) @$1.56/ft | 17.16
need 1/2" or 5/8" braided rope for lid gasket 55" long | 12
need 1/2" or 5/8" braided rope for door gasket 25" long | 6
TOTAL = | 201.86 | plus tax, shipping = $266
DENSITY OF MILD STEEL = | 7850 | KG/M3 = | 0.2836 | lb/in3
DENSITY OF STAINLESS STEEL = | 8000 | KG/M3 = | 0.2836 | lb/in3
DENSITY OF MILD STEEL = | 7850 | KG/M3 = | 0.2836 | lb/in3
DENSITY OF MILD STEEL = | 7850 | KG/M3 = | 0.2836 | lb/in3
DENSITY OF MILD STEEL = | 7850 | KG/M3 = | 0.2836 | lb/in3
CALCULATIONS - thicker metal from drawing specs:
PART:
Outer shell - 20ga mild steel | 72.8 | lb
lid alone - 1/8" stock | 29.7 | lb
hinges | 2 | lb
top plate - 1/8" stock